## User Stories
Genealogy Index Application Re-Write
User Story
ID | As a <type of user> | I want to <goal, objective> | so that <benefit, value, goal> | Priority | Status
1 | Public User | search by the person first and last name | I can order a copy of the person's obituary | 5 | Not Started |  | Priority
2 | Archives Staff Member | recieve an email after an order is placed | I can know when an order is placed | 4 | Not Started | System User Types | 5
3 | Archives Staff Member | preform CRUD operations on the DB without having to use Microsoft Access | I can have my data fields validated and don't have to directly enter data into the DB | 8 | Not Started | Public User | 4
4 | Archives Staff Member | be able to edit pricing for obituaries | I can edit pricing if needed | 4 | Not Started | System Administrator | 3
5 | Archives Staff Member | Add to a list of volunteers on a Special Thanks page | we give credit to those that helped | 4 | Not Started | Archives Staff Member | 2
6 | Public User | have a running total next to the shopping cart button | I can see what my total is with ease | 4 | Not Started | IT Service Desk Staff | 1
7 | Archives Staff Member | be able to preform CRUD operations (specifically UPDATE) on the DB from the Public Library | I can update typos / errors with data entry | 5 | Not Started
8 | Archives Staff Member | be able to add a county in the future | the database coverage area can be expanded |  | Not Started
9 | Archives Staff Member | be able to add a new newspaper in the future | newspapers from the new counties can be displayed |  | Not Started
10 | Archives Staff Member | be able to change the CSS of the Public User pages | the website can be kept fresh and up to UWSP Standards
11 | Public User | I want to be able to search by specific records (obits, census, nat) without having to sift through all records | I can see the records I'm interested in with ease
12 | Archives Staff Member | see the Terms of Service on the front page of user access | they are not hidden from the user prior to use
13 | Public User | have the View Cart button more obvious | I can find it more readily

## Project Backlog
Project Backlog
Task ID: | Task: | Priority: | Acceptance Criteria: | Status: | Story ID: | Comment
<Given - When - Then>
Landing View
L1 |  | 0 |  |  | 1
Priority
[7 empty] | 5 | Highest
4
Shopping Cart View | [6 empty] | 3
S1 | [6 empty] | 2
[7 empty] | 1 | Low
[7 empty] | 0 | Completed
Design/Documentaiton | [6 empty] | Status
E1 | [6 empty] | Completed
In Progress
Not Started
Cancelled
On Hold
Database
D1 | Develop database schema | 0 | Web application should be able to access/query the database. | Not Started | N/A
Testing
T1 | Generate a test plan | 0
T2 | Test new features from sprint (Each Sprint) | 0
T3 | User Acceptance Testing (Each Sprint) | 0
Other Programming Tasks
P1

## Sprint 2
Sprint 2 - (2/19/18 - 3/2/18)
Task ID: | Task: | Priority: | Assigned To: | Est Time: | Actual Time: | Start Date: | End Date: | Acceptance Criteria: | Status:

## Sprint 1
Sprint 1 - (2/5/18 - 2/16/18)
Task ID: | Task: | Priority: | Assigned To: | Est Time: | Actual Time: | Start Date: | End Date: | Acceptance Criteria: | Status:
Assigned To
Michael Bahde
Rudolph Dlobik